## Sheet1
Project Ironman | NR-7695
[5 empty] | June |  |  |  | July |  |  |  | August
Task | Owner | Target Date | Status | Comments | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
1. Choose a hosting site for Wordpress
Choose a hosting site | Lily/ Ken | 2019-06-14
Name Cheap ($16/year or $3/ month) |  |  |  | I'm more familiar with Name Cheap | bar: June Week 2
Blue Host ($15/year or $3/month) |  |  |  | Blue Host has a deal with Wordpress for a discount | bar: June Week 2
AWS (Amazon Web Services) |  |  | Done | We will be going with AWS! It is better for the website in the long run since it has more capabilities and services. Ken will help me set it up on 6/17 | bar: June Week 2
2. Connect domain to hosting site and install Wordpress
Connect our chosen hosting site to the domain name | Lily | 2019-06-17 | Done | bar: June Week 3
Install Wordpress | Lily | 2019-06-17 | Done | bar: June Week 3
3. Choose a theme
Meet with Ken and other supervisors for approval | Ken + supervisors | 2019-06-21 | Done | Details and customization of the theme is likely to change throughout the entire process | bar: June Week 3
4. Outline site map
Get information on tab and sub-tab titles from scientists | Brian, Margaret, and Guillaume | 2019-06-25 |  | Purpose of the site is to generate leads and educate, so website navigation should be based on this priority Questions to consider: -How many tabs is the most user friendly? (generally 5-7) -How many sets of subtabs do we want? (generally sites should not have more than 3) -titles of tabs and subtabs | bar: June Week 4
Create a document outlining tabs and subtabs | Lily | 2019-06-27 | bar: June Week 4
5. Gather information on general content
Work with Brian, Margaret, and Guillaume to get general information on what kind of content each page will have and how much content there will be | Brian, Margaret, and Guillaume | 2019-07-05 |  | In order for me to begin designing the wireframe of each page on the site, I need to have a general sense of content | bar: July Week 1
Think about key words for searching when coming up with content | Brian, Margaret, and Guillaume | 2019-07-02 |  | We want words that are popularly used in searches to gain traction with our audience members, rather than more technical terms that aren't as frequently searched | bar: July Week 1
6. Outline and implement wireframe
Hand draw sketches of each page | Lily | 2019-07-04 |  | Hand drawn sketches are easier for me to work efficiently since this is a time sensitive project | bar: July Week 1
First draft due to Jessica for comments | Jessica | 2019-07-04 | bar: July Week 1
Make adjustments | Lily | 2019-07-05 | bar: July Week 1
Second draft due to supervisors for comments | Supervisors | 2019-07-08 | bar: July Week 1 to July Week 2
Make adjustments | Lily | 2019-07-09 | bar: July Week 1 to July Week 2
Final draft due to supervisors | Supervisors | 2019-07-09 | bar: July Week 1 to July Week 2
Add wireframe to site | Lily | 2019-07-11 |  | During this process, I can also install some plugins that come with wordpress that can protect the security of the site, improve its speed and performance, backup info, and keep out spam. | bar: July Week 1 to July Week 2
7. Gather and upload content
Get content from scientists | Brian, Margaret, and Guillaume | 7/15/2019 to 7/22/2019 |  | With the site map and wireframe outlines established, I can begin working with the scientists again to gather detailed content (both worded information and diagrams/ images) Scientists can also give me information as they come up with it, rather than all at once. | bar: July Week 3
Create diagrams and images | Lily | 7/15/2019 to 7/26/19 |  | Have diagrams and images finished by this date- Scientists can give me instruction for creating diagrams throughout the whole process. | bar: July Week 3
Upload all content onto the site | Lily | 2019-07-22 | bar: July Week 3 to July Week 4
Meet with scientists and supervisors for comments | Scientists and Supervisors | 2019-07-23 | bar: July Week 3 to July Week 4
Make adjustments | Lily | 2019-07-25 | bar: July Week 3 to July Week 4
Meet with scientists and supervisors for comments | Scientists and Supervisors | 2019-07-26 | bar: July Week 3 to July Week 4
First draft of final site | Lily | 2019-07-30 | bar: July Week 3 to August Week 1
Final draft of final site | Lily | 2019-08-01 | bar: July Week 3 to August Week 1
8. Google Analytics
Sign up for Google Analytics | Lily | 2019-08-02 | bar: August Week 1
9. Testing
Test before the final launch | Lily and Jessica | 2019-08-08 | bar: August Week 2
Spelling, grammar, punctuation |  | 2019-08-08 | bar: August Week 2
Images are properly optimized |  | 2019-08-08 | bar: August Week 2
Content makes sense |  | 2019-08-08 |  | Does the site address the audience appropriately? | bar: August Week 2
Site speed |  | 2019-08-08 |  | Google has a site speed test we can use, which includes recommendations for improvements | bar: August Week 2
Mobile Friendly |  | 2019-08-08 |  | Images, text, hyperlinks, etc, all should transfer cleanly to mobile version | bar: August Week 2
Browser compatibility |  | 2019-08-08 |  | Internet Explorer, Firefox, Chrome | bar: August Week 2
Formatting |  | 2019-08-08 | bar: August Week 2
Navigation |  | 2019-08-08 |  | Ensure every possible journey through the website leads where it is supposed to lead | bar: August Week 2
Search bar |  | 2019-08-08 | bar: August Week 2
Other bugs |  | 2019-08-08 | bar: August Week 2
10. SITE LAUNCH |  | 2019-08-09